## Start Here
THE MONTH-END CLOSE CHECKLIST
What this is
A close that lands on day 18 runs every decision on stale numbers. This checklist is the fix in working form: a day-numbered calendar from five days before month end through day 7, one owner per task, dependencies named, and a flash report on day 3 so the business reads its numbers before the books are perfect.
Yellow cells are inputs. Status lights and the progress lines calculate. The task list ships filled with the standard close; rename, add, and delete rows to match your ledger.
The operating rules (from every fast close we have run)
1. Move work out of the close. Everything on the Pre-close days can be done before month end, and a close that starts on day 1 with reconciliations current is already half done.
2. One owner per task. A shared task is an unowned task. The owner column takes a name, not a department.
3. The day-3 flash is not optional. Revenue, margin, EBITDA estimate, cash. Decisions move on the flash; the close confirms it. Estimate the immaterial and say so.
4. Done means tied out with evidence, not checked off. The evidence column is where 'done' gets honest.
5. Lock the period at the close meeting. A close that reopens for stragglers is not closed.
Run it monthly (Metrics tab)
Enter the target close day and, each month, the actual. The days-to-close trend is the single best measure of whether the finance function is getting stronger: it should fall, then hold.
The blocked count is tomorrow morning's priority list. A task blocked two days running is the close's constraint; fix the input, not the deadline.
When the close holds at day 7 for three straight months, take a day out of the target. Speed is built one honest day at a time.
Where it leads
The day-8 owner report this close feeds has a working structure in our library, and the covenant check on day 5 is the covenant tracker doing its monthly job. Both are free at helm-advisory.com/resources. If your close is past day 10 and stuck, that is a 90-day fix we have done many times: start a conversation at helm-advisory.com.

## Close Calendar
THE CLOSE, DAY BY DAY
Phase | Day | Task | Owner | Depends on | Status | Evidence / tie-out
Pre-close | -5 | Bank and credit card reconciliations current through mid-month | Bookkeeper |  | Done
Pre-close | -5 | Fixed asset additions and disposals recorded to date | Bookkeeper |  | Done
Pre-close | -4 | Recurring journal entries drafted (depreciation, amortization, standard accruals) | Controller |  | Done
Pre-close | -3 | Customer billing current; unbilled work reviewed and invoiced | Billing |  | Done
Pre-close | -2 | Vendor invoices entered; missing-invoice list chased | AP |  | Done
Pre-close | -1 | Payroll accrual computed for the stub period | Controller |  | Done
Pre-close | -1 | Inventory cycle counts complete; large adjustments investigated before close | Ops + Controller |  | Done
Day 1-2 | 1 | Revenue cutoff: shipments/service through month end invoiced; next month kept out | Billing | Pre-close billing | Done
Day 1-2 | 1 | AP cutoff: received-not-invoiced accrual booked | AP |  | Done
Day 1-2 | 1 | Cash: all bank accounts reconciled to month end | Bookkeeper |  | Done
Day 1-2 | 2 | Payroll posted and reconciled to the payroll register | Controller |  | Done
Day 1-2 | 2 | Credit cards and employee expenses posted with receipts | AP |  | In progress
Day 1-2 | 2 | Inventory valuation rolled; COGS posted | Controller | Cycle counts | In progress
Day 3 | 3 | FLASH REPORT: revenue, gross margin, EBITDA estimate, cash, headcount to owner | Controller | Cutoffs done | Not started
Day 3 | 3 | Flash variances beyond threshold get one-line explanations | Controller | Flash report | Not started
Day 4-5 | 4 | Balance sheet reconciliations: AR aging ties to GL | Bookkeeper |  | Not started
Day 4-5 | 4 | Balance sheet reconciliations: AP aging ties to GL | AP |  | Not started
Day 4-5 | 4 | Prepaids and other assets rolled forward with support | Controller |  | Not started
Day 4-5 | 4 | Accrued liabilities reviewed; stale accruals released with reason | Controller |  | Not started
Day 4-5 | 5 | Debt schedule tied to statements; interest posted; covenant check run | Controller |  | Not started
Day 4-5 | 5 | Intercompany balances eliminated and settled (if applicable) | Controller |  | Not started
Day 4-5 | 5 | Non-routine entries reviewed with support attached | Controller |  | Not started
Day 6-7 | 6 | P&L variance review vs plan and prior month; explanations drafted | Controller + CFO | All recs | Not started
Day 6-7 | 6 | Balance sheet review: every account has an owner and a tie-out | CFO | All recs | Not started
Day 6-7 | 7 | Close meeting: open items dispositioned, entries locked, period closed | CFO | Reviews | Not started
Day 6-7 | 7 | Financial package handed to reporting (owner report ships day 8) | CFO | Close meeting | Not started

## Metrics
IS THE CLOSE GETTING FASTER?
Enter the target once and the actual each month. The trend is the health of the finance function in one number.
| Target close day (business days) | 7
| Flash report day | 3
| Month | Actual close day | vs target | Note (what slowed it)
| Feb | 16
| Mar | 14
| Apr | 12
| May | 10
| Jun | 9
Jul
Average of entered months
The example trend (16 to 9 days over five months) is the realistic shape of a close speed-up: two to three days per month of disciplined work, not a heroic leap. When it holds at target for three months, cut the target by one.