## Start Here
THE POST-ACQUISITION INTEGRATION RUNBOOK
What this is
The first hundred days of owning a business you just bought, in three working registers. The Hypothesis Tracker converts every diligence assumption into a number that gets verified against reality, because the most expensive words in M&A are 'the model assumed.' The Integration Plan runs the work by workstream and phase. The Synergy Register states the prize honestly, one-time costs and dis-synergies included.
Yellow cells are inputs. Progress lines and totals calculate.
Start with the hypotheses (day 1)
List every material assumption the price was built on: retention, pricing power, capex, add-backs, working capital. Record where each came from and the number that was assumed.
Then verify them in the first weeks, not the first year. Confirmed means the baseline holds. Adjusted means the value model moves and you now know by how much. Broken means act this week. The example ships with two broken hypotheses, because real deals have them.
This register is also your protection: earnout, escrow, and peg conversations go better with a dated, evidenced record of what was found and when.
Run the plan, honestly count the synergies
The Integration Plan is sequenced by phase: Day 1 items protect cash, people, and customers; nothing else matters until they hold. Assign one owner per line and work the phases in order. The progress line at the top tells the sponsor exactly where integration stands.
On the Synergy Register, book dis-synergies and one-time costs with the same seriousness as the savings. A synergy case without dis-synergies is a sales document, not a plan. Move items to Achieved only when the P&L shows them, the same two-month rule the value creation tracker uses.
Where it leads
The hypothesis tracker feeds the value creation plan; the day-100 numbers feed the first board pack. Both templates are in the library at helm-advisory.com/resources. If you want the hundred days run by people who have done it, start a conversation at helm-advisory.com.

## Hypotheses
DILIGENCE HYPOTHESIS TRACKER
Hypothesis (what the price assumed) | Source | Metric that proves it | Assumed | Actual | Status | Implication / action
Revenue retention holds through close | QoE report | Trailing 90-day revenue vs LTM run-rate | 95%+ | 96.4% | Confirmed | No action; watch the two accounts on notice
Pricing power of 3% annually | CIM / management | Realized price increase, first cycle | 3.0% | 2.0% | Adjusted | Value model reduced $120K/yr; escalator program accelerates the gap
Maintenance capex normalized at $400K | QoE report | TTM maintenance capex, verified | $400K/yr | $610K/yr | Broken | Deferred maintenance found on two lines; reprice year-1 plan, revisit reserve
Top customer renews at term | Management interviews | Contract executed | Renews | Renewed, 24 mo | Confirmed | Concentration still 18%; diversification stays on the VCP
Inventory is clean and current | Diligence data room | Excess & obsolete on day-1 count | Immaterial | $540K excess | Broken | Workdown launched; purchasing rules rewritten; peg dispute considered
Owner add-back of $310K is real | QoE report | Replacement cost of owner duties | $310K | $285K | Confirmed | GM hire absorbs duties at $95K less than owner comp plus bonus
Overtime normalizes to 8% post-close | Management plan | OT share of hours, day 90 | 8.0% | 11.2% | Adjusted | Three open roles are the cause; requisitions out, OT premium in bridge
Systems cutover inside 90 days | IT diligence memo | ERP migration complete | 90 days | 150 days (est.) | Adjusted | Parallel-run extended; close calendar protected by flash reporting

## Integration Plan
INTEGRATION PLAN BY PHASE
Workstream | Item | Phase | Owner | Status | Notes
Finance & cash | Bank accounts, signers, and treasury control transferred | Day 1 |  | Done
Finance & cash | 13-week cash forecast live for the combined entity | Week 1 |  | Done
Finance & cash | Payroll runs verified end to end, both entities | Day 1 |  | Done
Finance & cash | AP release rules and approval thresholds set | Day 1 |  | Done
Finance & cash | Covenant definitions read; reporting calendar to lender | Week 1 |  | Done
Finance & cash | Close calendar unified; day-3 flash defined | Day 30 |  | Done
Finance & cash | Working capital peg true-up prepared | Day 60 |  | Open
People | Day-1 communication delivered in person, both sites | Day 1 |  | Open
People | Retention conversations with the five keepers held | Week 1 |  | Open
People | Comp, benefits, and policy gaps mapped with dates | Day 30 |  | Open
People | Org chart to one page; every seat has one name | Day 30 |  | Open
People | First joint leadership cadence running weekly | Day 30 |  | Open
Customers | Top-10 customers called by the new owner personally | Week 1 |  | Open
Customers | Contract change-of-control clauses reviewed and cleared | Week 1 |  | Open
Customers | Pricing files consolidated; escalator rights mapped | Day 30 |  | Open
Customers | Service levels tracked weekly through transition | Day 30 |  | Open
Customers | Cross-sell list built from combined book | Day 60 |  | Open
Systems | Read-only access to all systems for the finance team | Day 1 |  | Open
Systems | Interim reporting bridge (two systems, one report) | Week 1 |  | Open
Systems | Migration plan with parallel-run dates | Day 30 |  | Open
Systems | Cutover executed with fallback tested | Day 100 |  | Open
Operations | Safety programs aligned; day-1 walkthrough done | Day 1 |  | Open
Operations | Combined ops KPI scoreboard live weekly | Week 1 |  | Open
Operations | Capacity and constraint map for the combined footprint | Day 30 |  | Open
Operations | Procurement overlap quantified; first renegotiations | Day 60 |  | Open
Operations | Footprint decision made with the numbers, not the emotion | Day 100 |  | Open
Legal & compliance | Insurance bound; certificates issued day 1 | Day 1 |  | Open
Legal & compliance | Licenses, permits, and registrations transferred | Day 30 |  | Open
Legal & compliance | Transition services agreement obligations calendared | Week 1 |  | Open
Legal & compliance | Earnout and escrow measurement rules documented | Day 30 |  | Open

## Synergies
SYNERGY REGISTER (HONEST VERSION)
Dis-synergies and one-time costs get booked with the same seriousness as the savings. Achieved means two consecutive months in the P&L.
Item | Type | Annual $ (+/-) | One-time cost | Confidence | Notes
Procurement overlap (top 12 vendors) | Cost synergy | 340000 | 15000 | High
Duplicate back-office roles (attrition-first) | Cost synergy | 280000 | 60000 | High
Facility consolidation, satellite warehouse | Cost synergy | 190000 | 220000 | Medium
Insurance and benefits program consolidation | Cost synergy | 110000 | 10000 | High
Cross-sell into acquired book | Revenue synergy | 320000 | 45000 | Medium
Customer overlap concessions (expected) | Dis-synergy | -180000 | 0 | Medium
Systems migration and parallel run | One-time only | 0 | 70000 | High
Net annual run-rate (synergies less dis-synergies)
Payback on one-time costs